## Sheet1
Task | Estimated completion date | Estimated time
1. Set up project environment and dependencies: | 2023-05-02 | 2-3 hours
Install Node.js, React, and Redux
Create project directory and set up project structure
Install necessary dependencies (e.g., react-router-dom, axios, etc.)
2. Create landing page: | 2023-05-03 | 6 hours
Design and create landing page layout
Add basic functionality (e.g., Navigation Bar, Login button, Register button)
3. Create login and registration pages: | 2023-05-04 | 8 hours
Design and create login and registration forms
4. Create job listing page: | 2023-05-08 | 10 hours
Design and create job listing page layout
Connecting mock JSON file for job postings data
View details to each job listing item
5. Implement job application and submission: | 2023-05-10 | 12 hours
Design and create job application page
Add functionality for job seekers to submit job applications
Saving of user application data into Firebase
6. Create user dashboard: | 2023-05-12 | 10 hours
Design and create user dashboard layout
Add functionality for users to manage job applications, saved job searches, etc.
7. Completion of the task: | 2023-05-15 | 8 hours
Testing the application and ensure all the Functional requirements are met
Validations
8. Add additional features: | 2023-05-18 | 10 hours
- Implementation of search bar to allow users to search for job postings by keyword or location.
- Adding the ability for users to save job postings to a list of favorites.
- Use React Router to implement client-side routing and allow users to navigate between different views of the application.